**Progress Meeting**

**Date:  April 14, 2021**

**Project Town and WIN:** Fryeburg       17280.01

The following were present:  MDOT – Beecher Whitcomb         Pratt –Brian Albert

1. **Progress since last meeting**: Continue installing new underdrain and basins, removed old drainage. Excavating roadway and driveways and placing new gravel, started milling of old pavement.
2. **Expected activities before the next meeting**: Continue subgrade and box-cutting drives, placing new gravel, continue milling of old pavement 79 to 95 +/-  and 109 to 125 +/-.
3. **Contractor’s Schedule of Work**: Slightly ahead on milling and driveway excavation.
4. **Payment Progress**: Estimate #11 was generated on April 2nd,  Est. #12 will be mid-April.
5. **Field Observations**:   Pratt has placed some signage and cones for Pedestrian traffic.
6. **Anticipated Traffic Delays or Related Issues**: Running alternating 1-way traffic through work zone with the use of flaggers.
7. **Updates to Pre-Construction Submittals**:  Mast Arm Submittals have been reviewed and sent back for revisions on calculations. Standard Traffic Submittals have been submitted and are under review. HMA submittals have been submitted and are also under review. HASP plan was resubmitted, reviewed and accepted April 9th.
8. **Contract Modifications, RFI’s, correspondence**:  None this week.
9. **Issues, Disputes, claims, concerns and resolutions:** Pratt had to skip a section of underdrain across Bradley Road due to a conflict with the new watermain that was installed last Fall. Coleman will be in next week to lower the new main as it was shown on their plans. We will be eliminating 2 entrances at the Bowling Alley as requested by owner.
10. **Project Safety**:  All good this week, Pratt has weekly Safety Meetings. A reminder was given to follow Gov. Mills safety rules.
11. **Utility Issues**:  CMP (On-Target) has been on-site switching power lines to new poles.
12. **Environmental**:  All looks good. Some touch-up needed at outflow at pipe Station 100 Lt.

This is an accurate summary of the meeting according to my records. Any authorized persons who take exception to

any statement in this report must notify the Resident in writing within five work days from receipt of this report, stating

in detail the comment, correction or omission. Otherwise, this report shall stand as written.

The next weekly meeting will be held on April 21st,  at 11:00 am at the MDOT Field Office.

Sincerely Yours,

                Beecher Whitcomb