**Progress Meeting**

**Date:  June 30, 2021**

**Project Town and WIN:** Fryeburg       17280.01

The following were present:  MDOT – Beecher Whitcomb          Pratt –Brian Albert

1. **Progress since last meeting**: Pratt and Son installed some new granite curb and placed HMA in front of new curb and completed subgrade/gravel operation on mainline, started some box-cut for sidewalks.
2. **Expected activities before the next meeting**: Possibly continue sidewalk boxcut and gravel and granite curb, grade gravel and place millings, Finegrade millings Tuesday & Wednesday.
3. **Contractor’s Schedule of Work**: Ahead on subgrade/gravel operations.
4. **Payment Progress**: Estimate #18 was generated on June 18th, Est. #19 will be end of week,
5. **Field Observations**:   Traffic volume has noticeably increased. Hazy, Hot, and Humid
6. **Anticipated Traffic Delays or Related Issues**: Running alternating 1-way traffic through work zone with the use of flaggers.
7. **Updates to Pre-Construction Submittals**:  Mast Arm Submittals have been reviewed and sent back for revisions on calculations. Standard Traffic Submittals have been submitted and were sent back for some revisions. AD Electric said the resubmittals should arrive this week.
8. **Contract Modifications, RFI’s, correspondence**:  None this week
9. **Issues, Disputes, claims, concerns and resolutions:** None this week from Contractor. Need Payrolls revised from Glidden for week ending 5/29, and from Pratt for week ending 6/12. Also time to start thinking about new sign submittals.
10. **Project Safety**:  All good this week, Pratt has weekly Safety Meetings.
11. **Utility Issues**: ProWire is showing up randomly and switched both Charter Lines and Consolidated lines to new poles, progressing nicely when here.
12. **Environmental**:  All looks good. Using water for dust control.

This is an accurate summary of the meeting according to my records. Any authorized persons who take exception to

any statement in this report must notify the Resident in writing within five work days from receipt of this report, stating

in detail the comment, correction or omission. Otherwise, this report shall stand as written.

The next weekly meeting will be held on July 7th,  at 10:00 am at the MDOT Field Office.

Sincerely Yours,

                Beecher Whitcomb