**Progress Meeting**

**Date:  July 30, 2020**

**Project Town and WIN:** Fryeburg       17280.00

            The following were present:  MDOT—Beecher Whitcomb      Reed & Reed---Jim Whorff      Coleman---Rick Couture

1. **Progress since last meeting**: Grading new gravel, placement of millings and finegraded millings for  FDR, placed base pavement on areas of FDR that were ready, Started installing Bit. curb and more guardrail, shaping inslopes and ditches.
2. **Expected activities before the next meeting**: Continue finegrading of millings, complete the process of FDR, start grading of shoulders, raise basins and start granite curb, general cleanup.
3. **Contractor’s Schedule of Work**: Slightly behind on curb, FDR and paving.
4. **Payment Progress**: Estimate #39 was generated July 24th, Estimate #40 will be next week.
5. **Field Observations**: Traffic volumes have noticeably increased.
6. **Anticipated Traffic Delays or Related Issues**: Running alternating 1-way traffic through work zone with the use of flaggers.
7. **Updates to Pre-Construction Submittals**:  Request for Traiano as a sub for hand-placed HMA has been approved, still waiting for ACE as flagging sub that was submitted Tuesday July 28th.
8. **Contract Modifications, RFI’s, correspondence**:  None this week.
9. **Issues, Disputes, claims, concerns and resolutions**:  None this week.
10. **Project Safety**:  All good this week, Coleman has weekly Safety Meetings.
11. **Utility Issues**:  CMP looked at poles of concern and said they were not on the poles. Consolidate has stated they should be here this week to work on the pole issues.
12. **Environmental**:  All looks good. Project held up well in the hard rain.

This is an accurate summary of the meeting according to my records. Any authorized persons who take exception to

Any statement in this report must notify the Resident in writing within five work days from receipt of this report, stating

In detail the comment, correction or omission. Otherwise, this report shall stand as written.

The next weekly meeting will be held on August 6th, at 10:00am at the MDOT Field Office.

Sincerely Yours,

                Beecher Whitcomb----Resident